## Sheet1
RISK MANAGEMENT MATRIX
NAME | Retail & E-Commerce Demand Forecasting with Inventory Management |  |  |  | OBJECTIVE | Provide a robust, scalable system for accurate demand forecasts and efficient inventory control, while minimizing technical, data, and operational risks.
REF / ID | P R E - M I T I G A T I O N |  |  |  | DEPARTMENT / LOCATION | MITIGATIONS / WARNINGS / REMEDIES | P O S T - M I T I G A T I O N
| RISK | RISK SEVERITY | RISK LIKELIHOOD | RISK LEVEL |  |  | RISK SEVERITY | RISK LIKELIHOOD | RISK LEVEL | ACCEPTABLE TO PROCEED?
|  | – ACCEPTABLE – TOLERABLE – UNDESIRABLE – INTOLERABLE | – IMPROBABLE – POSSIBLE – PROBABLE | – LOW – MEDIUM – HIGH – EXTREME |  |  | – ACCEPTABLE – TOLERABLE – UNDESIRABLE – INTOLERABLE | – IMPROBABLE – POSSIBLE – PROBABLE | – LOW – MEDIUM – HIGH – EXTREME | YES / NO
R1 | System Integration Issues (modules, APIs may fail or be incompatible) | INTOLERABLE | POSSIBLE | HIGH | IT / Development | - Modular development and testing | TOLERABLE | IMPROBABLE | LOW | YES
- Standardized APIs
- Automated integration testing
R2 | Scalability & Performance (high traffic or data volume) | UNDESIRABLE | POSSIBLE | MEDIUM | IT / Operations | - Load/stress testing | TOLERABLE | IMPROBABLE | LOW | YES
- Scalable cloud infrastructure (AWS/GCP)
- Caching (CDN) & microservices architecture
R3 | Deployment & Downtime (unexpected outages) | INTOLERABLE | POSSIBLE | HIGH | IT / DevOps | - CI/CD pipelines for automated deployments | TOLERABLE | IMPROBABLE | LOW | YES
- Staging environment testing
- Backup & rollback procedures
R4 | Data Quality & Availability (inaccurate or missing data) | UNDESIRABLE | PROBABLE | HIGH | Data Management | #NAME? | TOLERABLE | POSSIBLE | LOW | YES
- Multiple data sources & backups
- Regular data audits and cleaning
R5 | Model Training & Overfitting (poor forecasting accuracy) | UNDESIRABLE | POSSIBLE | MEDIUM | Data Science / Analytics | - Cross-validation & periodic retraining | TOLERABLE | IMPROBABLE | LOW | YES
- Monitor performance metrics (MAE, RMSE)
- Early detection of model drift
R6 | User Adoption & Training (low adoption of new system) | TOLERABLE | POSSIBLE | MEDIUM | Operations / HR | - Comprehensive training programs | ACCEPTABLE | IMPROBABLE | LOW | YES
- Dedicated support channels
- Iterative UX improvements based on feedback
R7 | Security & Compliance (risk of data breach or unauthorized access) | INTOLERABLE | POSSIBLE | HIGH | IT / Security | - Robust authentication (JWT), role-based access | TOLERABLE | IMPROBABLE | LOW | YES
- SSL/TLS encryption
- Regular security audits & penetration testing
R8 | Timeline & Resource Constraints (delays, limited resources) | UNDESIRABLE | POSSIBLE | MEDIUM | Project Management | - Agile methodology (sprints & stand-ups) | TOLERABLE | IMPROBABLE | LOW | YES
- Buffer time in project plan
- Clear communication & documentation